## MDR
Project Name |  |  | @projects_control
Item No | Discipline | Document No | Document Type | Document Title | Planned Issue Date | Last date of Contractor | Last date of Consultant | Revision |  | 1st Issue | [5 empty] | 2nd Issue | [5 empty] | W.F |  | Steps % |  |  |  | Progress %
[8 empty] | Last Rev of Contractor | Last Status of Consultant | Contractor |  |  | Consultant |  |  | contractor |  |  | Consultant |  |  | Level1 | Level2 | Start | Issue For Approval | Client Comments | AFC
[10 empty] | Letter No | Date | Rev | Letter No | Date | Status | Letter No | Date | Rev | Letter No | Date | Status |  |  | 20 | 50 | 80 | 100
Engineering | [21 empty] | 100% | [5 empty] | 59.78%
CIVIL | [21 empty] | 24% | [5 empty] | 100%
50 | EA | GTG-216-22-EA-DW-010 | DWG | floor plan & roof plan (Omidiyeh pump station - control room) | 94/10/26 | 94/11/15 | 94/11/27 | 2 | AFC | 4289 | 94/11/03 | 1 | 31044 | 94/11/10 | COM. | 4379 | 94/11/15 | 2 | 32404 | 94/11/27 | AFC |  | 10% | 20% | 50% | 80% | 100% | 100%
51 | EA | GTG-216-22-EA-DW-011 | DWG | section A & elevations a,b(Omidiyeh pump station - control room) | 94/10/26 | 94/11/15 | 94/11/27 | 2 | AFC | 4289 | 94/11/03 | 1 | 31044 | 94/11/10 | COM. | 4379 | 94/11/15 | 2 | 32404 | 94/11/27 | AFC |  | 20% | 20% | 50% | 80% | 100% | 100%
52 | EA | GTG-216-22-EA-DW-012 | DWG | section B & elevations c,d (Omidiyeh pump station - control room) | 94/10/26 | 94/11/15 | 94/11/27 | 2 | AFC | 4289 | 94/11/03 | 1 | 31044 | 94/11/10 | COM. | 4379 | 94/11/15 | 2 | 32404 | 94/11/27 | AFC |  | 30% | 20% | 50% | 80% | 100% | 100%
53 | EA | GTG-216-22-EA-DW-013 | DWG | False Floor & False ceiling & enlarged planse | 94/10/27 | 94/11/15 | 94/11/27 | 2 | AFC | 4289 | 94/11/03 | 0 | 31044 | 94/11/10 | COM. | 4379 | 94/11/15 | 2 | 32404 | 94/11/27 | AFC |  | 40% | 20% | 50% | 80% | 100% | 100%
MECHANICAL | [21 empty] | 33% |  | 0% | 0% | 0% | 0% | 98%
313 | EM | GTG-216-22-EM-DS-01 | DS | Storage Tank Mechanical Data sheet for relief tank TK-2001/2101 | 94/11/08 | 94/11/27 | 95/01/28 | 2 | COM. | 4331 | 94/11/10 | 1 | 31991 | 94/11/19 | COM. | 4437 | 94/11/27 | 2 | 1575 | 95/01/28 | COM. |  | 10% | 20% | 50% | 80% |  | 80%
314 | EM | GTG-216-20-EM-DS-03 | DS | Centrifugal pump data sheet crude oil transfer pump P-2001 A/B/C | 94/11/19 | 95/03/23 | 95/03/29 | 2 | AFC | 4419 | 94/11/20 | 1 | 1575 | 95/01/28 | COM. | 5122 | 95/03/23 | 2 | 7895 | 95/03/29 | AFC |  | 15% | 20% | 50% | 80% | 100% | 100%
315 | EM | GTG-216-21-EM-DS-01 | DS | Centrifugal pump data sheet crude oil transfer pump P-2101A/B/C | 94/11/19 | 95/03/23 | 95/03/29 | 2 | AFC | 4419 | 94/11/20 | 1 | 1575 | 95/01/28 | COM. | 5122 | 95/03/23 | 2 | 7895 | 95/03/29 | AFC |  | 25% | 20% | 50% | 80% | 100% | 100%
316 | EM | GTG-216-22-EM-DS-05 | DS | Centrifugal pump data sheet reinjection pump P-2003 A/B | 94/11/19 | 95/03/23 | 95/03/29 | 2 | AFC | 4419 | 94/11/20 | 1 | 1575 | 95/01/28 | COM. | 5122 | 95/03/23 | 2 | 7895 | 95/03/29 | AFC |  | 25% | 20% | 50% | 80% | 100% | 100%
317 | EM | GTG-216-22-EM-DS-06 | DS | Data sheet for Waste Water Transfer Pump. P-2004 | 94/11/08 | 94/11/21 | 95/01/28 | 2 | AFC | 4321 | 94/11/07 | 1 | 31727 | 94/11/17 | - | 4410 | 94/11/21 | 2 | 1568 | 95/01/28 | AFC |  | 25% | 20% | 50% | 80% | 100% | 100%
ELECTRICAL & CATHODIC | [21 empty] | 43% |  | 0% | 0% | 0% | 0% | 8%
357 | ED | GTG-216-22-ED-CN-02 | CN | Cathodic Protection For Under Ground Pipes Omidieh Pump Station | 95/02/07 | 95/04/01 | 95/04/14 | 2 | COM. | 4875 | 95/02/15 | 1 | 5926 | 95/03/09 | Rej. | 5146 | 95/04/01 | 2 | 9445 | 95/04/14 | COM. |  | 10% | 20% | 50% | 80% | 0% | 80%
358 | EE | GTG-216-22-EE-CN-01 | CN | Lighting System Calculation Note | 95/01/10 | 95/01/29 | 95/02/25 | 1 | COM. | 4726 | 95/01/29 | 1 | 4373 | 95/02/25 | COM. | [7 empty] | 5% | 0% | 0% | 0% | 0% | 0%
359 | EE | GTG-216-44-EE-CN-02 | CN | Earting and Lightning Sys.Calculation Note | 95/02/02 | 0 | 0 | 0 | 0 | [13 empty] | 10% | 0% | 0% | 0% | 0% | 0%
360 | EE | GTG-216-44-EE-CN-03 | CN | CABLE SIZING CALCULATION NOTE | 95/02/11 | 0 | 0 | 0 | 0 | [13 empty] | 15% | 0% | 0% | 0% | 0% | 0%
361 | EE | GTG-216-44-EE-CN-04 | CN | CALCULATION FOR AC/DC NO BREAK SYSTEM | 95/02/08 | 0 | 0 | 0 | 0 | [13 empty] | 5% | 0% | 0% | 0% | 0% | 0%
362 | ED | GTG-216-22-ED-DS-01 | DS | Data Sheet For Cathodic Protection | 95/02/12 | 0 | 0 | 0 | 0 | [13 empty] | 13% | 0% | 0% | 0% | 0% | 0%
363 | EE | GTG-216-22-EE-DS-04 | DS | DATA SHEET FOR SQUIRREL CAGE INDUCTION MOTORS | 95/02/14 | 0 | 0 | 0 | 0 | [13 empty] | 17% | 0% | 0% | 0% | 0% | 0%
364 | EE | GTG-216-44-EE-DS-03 | DS | DATA SHEET FOR EMERGENCY DIESEL GENERATOR | 95/02/15 | 0 | 0 | 0 | 0 | [13 empty] | 25% | 0% | 0% | 0% | 0% | 0%